## Sheet1
Group 4: Nathan Blaubach, Peter Emery, John Hunter and Scott Schroeder
Number | Category | Title | Story | Acceptance Criteria | Criticality | Subtasks | Est. Hours | Release | Implemented | Notes
S.UI.1 | User Input | Filter Based Search | As a teller, I need to be able to search for flight paths and hotel rooms using multiple filters, So that I can find the items I want faster. | 1. Must be able to filter by: Date, Time, Destination, Cost | 5 | Create Database: 8 Create Search: 4 | 12 | R1 | 100% | Creating Database took much longer than expected, subtasks added at end of release 1 due to misunderstanding story book requirements
S.UI.2 | User Input | Reserve Items | As a teller, I need to be able to reserve seats/rooms for my customer, So that I can make sure my customer gets what he/she wants/will be paying for. | 1. Can reserve a room or seat 2. Displays confirmation message for the reservation | 5 | Create GUI: 4 Create Reservation: 6 | 10 | R1 | 100% | Fairly correct on time estimation, subtasks added at end of release 1 due to misunderstanding story book requirements
S.UI.3 | User Input | Cancel Reservation | As an teller, I need to be able to cancel reservations for my customers, So that I can use the service more dynamically, and avoid conflicts. | 1. User must be able to cancel a current order | 4 | Create GUI: 2 Back End: 3 | 6 | R1 | 100% | Moved from release 1 to release 2 due to running out of time Removed mentions of email comfirmation, not nessesary for project scope
S.UI.4 | User Input | Administrative Access | As an system administrator, I need to have administrative access to the data, So that I can adjust/add/remove items for sale. | 1. Must be able to: Add, Remove, and Edit Items 2. Any data for sales should be accessable | 3 | Read From File: 2 Write To File: 2 GUI: 2 DB Edit : 6 | 12 | R2 | 50% | Reading and writing to file complete Functional GUI and DB editing dropped due to it not being needed to meet the system requirements
S.SO.1 | System Output | Generate Itinerary | As a teller, I need to generate an itinerary about my customers reservation, So that my customer can accept their reservation, and receive information based on their reservation which is necessary to prevent errors. | 1. Teller must be able to generate an itinerary for a customer 2. The itinerary generated by the teller must be printable | 4 | Itinerary: 3 GUI: 1 | 4 | R2 | 100% | Removed mentions of emailing, not nessesary for project scope
S.SO.2 | System Output | Receipt | As a teller, I need to generate a receipt based on paymen,t So that I can inform my customer of the cost of their reservation. | 1. The receipt is displayed to the teller 2. The receipt must be printable | 4 | Receipt: 3 GUI: 1 | 4 | R2 | 100% | Removed mentions of emailing, not nessesary for project scope
S.SO.3 | System Output | Multistage Flight | As a Teller, I need a system that can handle multistage flights, So that I can inform my customer of the shortest, cheapest, and time-relevant route for their flights. | 1. Must implement a shortest path algorithm to determine shortest path between locations. 2. Must be able to find the cheapest tickets for a multistage flight between locations. 3. Must be able to find a multistage flight that is time-relevant, meaning the flight(s) occur during an appropriate time according to other items on a reservation. | 3 | Domain Refactoring: 5 Search Imp/Test: 7 | 12 | R3 | 100% | This is implemented with methods decomposed correctly
S.UI.5 | User Input | Undo Actions | As a Teller, I need to be able to undo my recent actions, so that I can correct any mistakes that I could make while going through the reservation process. | 1. Must be able to undo actions during the reservation process | 3 | Undo Action: 5 | 5 | R3 | 100% | Is implemented, but will want to make slight changes later depending on GUI changes.
[5 empty] | Total: |  | 65